ARMENIA TOURISM AND REGIONAL INFRASTRUCTURE IMPROVEMENT

PROJECT

STAKEHOLDER ENGAGEMENT PLAN

ARMENIAN TERRITORIAL DEVELOPMENT FUND

ARMENIA TOURISM AND REGIONAL INFRASTRUCTURE

PROJECT

STAKEHOLDER ENGAGEMENT PLAN

JANUARY, 2026

Prepared by Armenian Territorial Development Fund

Updated based on stakeholder consultations carried out on February 25, 2025 at the national level and during August–September 2025

at the local level

CONTENTS

ACRONYMS	v

1.	INTRODUCTION	6

1.1.	Project Description	6

1.1.1	Activities/Components	6

1.1.2 Implementing Agencies	8

1.1.3 Prior Stakeholder Engagement Activities during Project Preparation	8

1.2.	Objective and Scope of the Stakeholder Engagement Plan	10

1.3.	Principles	12

1.4.	Limitations	13

2.	STAKEHOLDER IDENTIFICATION AND ANALYSIS	18

2.1.	Key definitions and main stakeholder groups	18

2.2.	Potentially Affected Parties	19

2.3	Other Interested Parties	21

2.4	Disadvantaged and/or Vulnerable Groups	23

2.5	Modalities for Engagement	24

3.	STAKEHOLDER ENGAGEMENT ACTIVITIES AND INFORMATION DISCLOSURE DURING PROJECT IMPLEMENTATION	26

3.1.	Summary of Stakeholder Engagement during Preparation of the Stakeholder Engagement Plan	26

3.2.	Information Disclosure	27

3.3.	Resources and Responsibilities	30

3.3.1 Management functions and responsibilities	30

3.3.2 Resources	30

4.	FEEDBACK and Grievance Redress Mechanism	31

4.1.	Introduction to Feedback and Grievance Redress Mechanism	31

4.2	Grievance Records and Documentation	32

4.3 Closure of Grievances	32

4.4 Communicating FGRM to the Project Stakeholders	34

4.5 Sexual Exploitation and Abuse and Sexual Harassment Grievances	34

4.6	Grievance Resolution	35

ANNEX 1. PLANNED STAKEHOLDER ENGAGEMENT ACTIVITIES	36

ANNEX 2. THE FGRM FOCAL POINTS AND THE FGRM COORDINATOR’S CONTACT INFORMATION PUBLICATION FORM	40

ANNEX 3. THE GRIEVANCE REGISTRATION LOG	41

ANNEX 4. SEP BUDGET	42

Annex 5. INSTITUTIONAL ARRANGEMENTS FOR THE LOCAL WORKING GROUP (Subject to revision after the Project Operational Manual approval)	43

ANNEX 6. MINUTES OF PUBLIC CONSULTATIONS MEETING ON ENVIRONMENTAL AND SOCIAL INSTRUMENTS FOR ARMENIA TOURISM AND REGIONAL INFRASTRUCTURE PROJECT	45

# ACRONYMS

| ATDF | Armenian Territorial Development Fund |
| --- | --- |
| AUA | American University of Armenia |
| CDP | Cluster Development Plan |
| CHMP | Cultural Heritage Management Plan |
| CH | Cultural Heritage |
| CLO | Community Liaison Officer |
| CSO | Civil society organization |
| DMO | Destination Management Office |
| EIA | Environmental Impact Assessment |
| EIEC | Environmental Impact Expertise Center |
| E&S | Environmental and Social |
| ESCP | Environmental and Social Commitment Plan |
| ESIA | Environmental and Social Impact Assessment |
| ESF | Environmental and Social Framework |
| ESHS | Environmental, Social, Health and Safety |
| ESMF | Environmental and Social Management Framework |
| ESMP | Environmental and Social Management Plan |
| ESR | Environmental and Social Review |
| ESS | Environmental and Social Standards |
| FGRM | Feedback and Grievance Redress Mechanism |
| GoA | Government of Armenia |
| GRC | Grievance Redress Committee |
| H&S | Health and Safety |
| LEIDP | Local Economy and Infrastructure Development Project |
| LMP | Labor Management Procedures |
| LSGB | Local Self-Governance Body |
| LWG | Local Working Group |
| MoE | Ministry of Economy |
| M&E | Monitoring and Evaluation |
| MoEnv | Ministry of Environment |
| NGO | Non-governmental organization |
| PAP | Project Affected Person |
| PC | Public Consultation |
| POM | Project Operational Manual |
| PPP | Public-Private Partnership |
| PSC | Project Steering Committee |
| PT | Project Team |
| RoA | Republic of Armenia |
| RF | Resettlement Framework |
| RP | Resettlement Plan |
| SEP | Stakeholder Engagement Plan |
| SME | Small and Medium Enterprises |
| SNCO | State Non-Commercial Organization |
| TC | Tourism Committee |
| TRIP | Tourism and Regional Infrastructure Project |
| WB | World Bank |

# INTRODUCTION

Armenia Tourism and Regional Infrastructure Project (or hereafter “TRIP”) will support activities and interventions for sustainable, inclusive, and climate and natural-disaster resilient tourism in seven prioritized clusters of Areni, Dilijan, Dvin,  Goris, Gyumri, Jermuk and Yeghegis. The development objective of the Project is to improve access to sustainable, resilient and climate smart infrastructure services for increased tourism contribution to the local economy of project-supported clusters in Armenia. The main interventions would seek to address the key constraints to tourism development in each of the clusters, including a lack of basic and quality infrastructure and services, and a need to diversify the offerings and develop the respective main niches identified under the Government of Armenia (GoA) cluster approach. The proposed Project will also follow-on and build on the investments, experience, and lessons learned under the implemented Local Economy and Infrastructure Development Project (LEIDP).

This Stakeholder Engagement Plan (SEP) has been prepared to guide relevant stakeholder engagement activities both during the project preparation and implementation.

The draft SEP was disclosed on October 10, 2025. The document was updated based on stakeholder consultations carried out on February 25, 2025, at the national level and during August–September 2025 at the local level.

## Project Description

### Activities/Components

The objectives of the Project are to improve access to climate-resilient infrastructure and increase tourism contribution to the local economy of Project-Supported Clusters in Armenia.

The Project consists of the following components:

Component 1.	Fostering Integrated and Sustainable Cluster Development

- Preparation and finalization of Cluster Development Plans (CDPs) for Dilijan, Dvin, Goris, Jermuk, and Yeghegis.

- Preparation of climate and disaster resilient zoning and master plans, investment planning studies, and other analytical works required to inform the preparation and finalization of the CDPs under Part 1(a) of the Project.

- Implementation of public awareness campaigns and associated citizen engagement activities during the preparation of CDPs and after the approval of the CDPs by the Project Steering Committee (PSC) to foster local ownership, inform future urban and spatial planning, and support decision-making.

- Preparation of operational and maintenance plans for tourism assets and site management plans for cultural heritage (CH) sites for long-term monitoring and preservation of the touristic assets.

- Conducting surveys and other tourism data acquisition activities for the collection of anonymized information and reporting of local tourism statistics through tourism stakeholders, such as the Tourism Committee (TC) and local Destination Management Offices (DMO).

- Provision of training, capacity building, goods, and equipment to support the establishment and operations of DMOs in Areni, Dilijan, Yeghegis, and Jermuk.

- Implementation of leadership training activities and the promotion of local participation of women to assume leadership roles in decision-making bodies within the tourism value chain, including through increasing women representation in Local Working Groups (LWG) under the Project and provision of necessary capacity building and skills enhancement activities for women.

Part 2. Supporting Climate-Resilient Infrastructure and Promoting Private Sector Participation

2.1.	Rehabilitating and upgrading infrastructure and services: carrying out Site-Specific Activities for the purposes of improving basic and tourism-related infrastructure and urban upgrading to improve access to touristic sites and surrounding areas, including, inter alia:

- improvement of the quality, resilience, and condition of roads and transport-related infrastructure and promotion of the adoption of green and eco-friendly alternative modes of transportation through the resilient construction, rehabilitation, improvement, and/or maintenance of existing roads and bridges, expansion of pedestrian zones, streetscaping and installation of light-emitting diode street lighting, and use of other green infrastructure elements for climate resilience and for enhancing the attractiveness of streets, access roads, and parking areas;

- climate-resilient upgrading of basic infrastructure and services and rehabilitation of municipal infrastructure through the improvement of existing local water supply connections, rehabilitation and upgrading of sewerage systems and wastewater collection and discharge systems, improvements for proper storm management, and resilient rehabilitation and/or upgrading of telecommunications infrastructure to improve digital access and connectivity of local communities and businesses, including ensuring availability of network connectivity to enable communications before and after disaster events;

- enhancement of the attractiveness of public areas and spaces through the rehabilitation and/or expansion of green spaces, public park upgrading, streetscaping, and the provision of related urban amenities for satisfactory touristic experiences;

- provision of climate-resilient tourism-related infrastructure and services through the construction or rehabilitation of tourism facilities, such as DMOs and museums, and the preservation and improvement of CH assets; and

- provision of support for public-private investments through the provision of complementary climate-resilient public infrastructure improvements to attract private investments, such as the construction or rehabilitation of public facilities, roads and streets, water and sanitation, and telecommunications that are located adjacent to commercial investment sites.

2.2.	Fostering private sector participation, enhancing professional skills, and enabling job creation: promotion of the Project-Supported Clusters and increasing the participation of local firms and individuals in the tourism sector for local economy development through:

- provision of support for branding, marketing, and promotion activities within the tourism value chain;

- promotion of Public-Private Partnership (PPP), including the assessment, design, and preparation of potentially viable PPPs to be identified under the CDPs;

- provision of professional skills development in the hotel, restaurant, and catering sector for local workers involved in tourism and tourism-related business, with priority given to vulnerable and disadvantaged groups;

- provision of on-the-job training, career counseling, and formal learning in the hotel, restaurant, and catering sector;

- delivery of training and capacity building activities in business idea incubation, business planning, investor pitching, developing branding, marketing, and sales strategies, and administrative processes to facilitate business registration and compliance for local tourism firms and entrepreneurs, including targeted support for women-led businesses;

- development of studies and analytical work to design, implement, and/or monitor activities for fostering creation of job opportunities in the tourism sector across the Project-Supported Clusters.

- development and/or promotion of digital tools, such as software applications for providing real-time information on transportation options, events, calendars of festivals, available amenities, hiking trails, and tour builders as well as timely communication of climate hazards such as wildfires, landslides, and extreme temperature warnings.

Part 3.		Program Management and Operational Support

Provision of support for the Project Implementing Entity to manage the Project and ensure that all Project activities meet the Bank requirements on environmental, social, fiduciary, procurement, and technical standards, carry out monitoring and evaluation activities, and enhance capacities through training and knowledge sharing activities.

Part 4. 		Contingent Emergency Response Component

Provision of immediate response to an Eligible Crisis or Emergency, as needed.

### 1.1.2 Implementing Agencies

The Ministry of Economy (MoE) will provide the overall decision making and strategic leadership of the Project. The TC, under the MoE, serves as the primary government agency with the mandate for tourism development and promotion in the country. In this capacity, the TC will play a critical role of supporting the formulation and identification of investments under the project, and will be the main counterpart in the MoE responsible for coordination and policy support across the project.

The Armenian Territorial Development Fund (ATDF) will serve as the Project Implementing agency. ATDF will be responsible for the execution of all project activities and fiduciary responsibilities, including procurement and financial management, environment and social (E&S) monitoring, and all related responsibilities regarding technical assessment, design, and civil works, including works supervision, monitoring and evaluation (M&E), and reporting.

### 1.1.3 Prior Stakeholder Engagement Activities during Project Preparation

The TC conducted prior stakeholder engagement activities and consultation meetings during the project identification and preparation with the aim to select the clusters for the project. Consultation meetings were held in several regions (marzes) of Armenia with participation of representatives of municipality administrations, the local tourism sector, DMOs and private sector (see photos from one of the consultation meetings in Annex 1). These consultations, alongside discussions with local authorities, community representatives, and technical experts, helped guide the selection of activities under each sub-component, ensuring that the proposed interventions align with the needs and priorities of the communities, and ensure complementarity with existing and planned interventions on the private sector side.

The selection of the 7 clusters was made based on the several criteria matrix that was developed together with the World Bank (WB) team. The list of criteria included:

  - tourism and regional development priorities of the Government,

  - accessibility from the main entry points to Armenia (land and air borders),

  - presence of a functional DMO to promote the proposed cluster sustainably,

  - opportunities for the private sector involvement,

  - capitalizing on the recently completed and ongoing tourism investments to increase synergies, including the  investments under LEIDP,

  - economic viability and return on investments,

  - high potential for developing niche and sub-niche tourism offerings, to increase the diversification of Armenia’s overall tourism offers.

During the preparation of the cluster development concepts under the LEIDP, a preliminary list of stakeholders was developed to guide the design of engagement activities. This list was informed by a series of consultations with key actors across the tourism, regional development, municipal, and private-sector domains. Inputs were collected through meetings, workshops, and bilateral discussions conducted with national and local government representatives, community leaders, sector associations, civil society organizations (CSO), service providers, and private enterprises operating in the targeted clusters.

In the Project preparation phase the following activities were conducted by the experts hired by the WB to ensure participatory inclusion of women in discussing socioeconomic issues related to tourism development of their region/community, as well as to engage representatives of local business community operating in tourism sector in identifying key obstacles and main directions of development of tourism-related sectors:

- On May 24, an online discussion was conducted with the DMOs. The female-managers of 4 DMOs (Goris, Dilijan, Gyumri and Yeghegnadzor) have presented common issues and local specifics of tourism-related sectors in their regions/cities with emphasizing employment opportunities for women, youth, elderly and gaps in their professional knowledge and skills. The recommendations were summarized by two groups: specific for their regions (Syunik, Tavush, Shirak and Vayots Dzor) and general which are common to the entire tourism industry.

- On June 21, an online discussion was conducted with members of WINNET (Women Resource Centers non-governmental organization (NGO) Network). The founders/leaders of 7 WINNET member NGOs discussed the necessary measures to promote women's participation and entrepreneurship in tourism related sectors. The participants highlighted also the role that the WINNET Armenia network plays in supporting employment of women and socially vulnerable people, including trough creating social enterprises  (e.g. handicrafts, souvenirs, master classes, etc.).

- In July-August 2024, survey was conducted including the businesses operating in 7 target clusters. The lists of 116 business-organisations with contacts of their heads/managers were provided by 4 DMOs and 2 Regional Governments (Ararat and Aragatsotn marzpetarans). The selection of business-organisations to be surveyed was conducted based on a) diversification of tourism-related businesses, and b) willingness of the selected businesses to fill in a questionnaire. The survey was conducted through e-mails based on the preliminary developed questionnaire. Due to internet/communication problems of some of survey-participants, 4 interviews were conducted by phone. In total, 34 questionnaires were filled in, the survey database was created and used for preparation of summary tables and analysis of data.

To address the identified gaps, the Project aims to create inclusive, gender-responsive programs that enhance opportunities for both women and youth in tourism-related sectors, as employees and entrepreneurs. By partnering with local communities, self-governments, and various organizations, the project will support the development of formal employment incorporating women’s preferences, needs, and design contributions through a participatory gender-inclusive process.

This SEP also builds on the engagement activities previously undertaken by the MoE, TC, ATDF, and Local Self-Governance Bodies (LSGB) in the frames of the LEID project. Such engagement activities included:

- Identifying and categorizing stakeholders;

- Conducting stakeholder mapping and analysis;

- Providing clear and timely information while improving communication flow;

- Ensuring transparency about actions being taken and how others can contribute;

- Listening to stakeholders and understanding their needs and interests;

- Offering opportunities for involvement that make efficient use of time and resources, allowing stakeholders to provide meaningful input.

## Objective and Scope of the Stakeholder Engagement Plan

The TRIP Project is being prepared under the WB’s Environmental and Social Framework (ESF). In line with Environmental and Social Standard 10 on Stakeholder Engagement and Information Disclosure (or hereafter ESS), the implementing agencies should provide stakeholders with timely, relevant, understandable, and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination, or intimidation.

The overall objective of this SEP is to define a program for stakeholder engagement, including public information disclosure and consultation throughout the entire project cycle. The SEP outlines the ways in which the project implementing agency will communicate with stakeholders and includes a mechanism by which people can raise concerns, provide feedback, or make complaints about project activities or any activities related to the project.

The SEP covers the overall project activities, prioritizing those with potential E&S risks. However, entry points will be explored in the areas where development opportunities can be pursued through the project’s resources.

Sub-project and/or site-specific level engagement will be integrated as part of the overall design and implementation of the activities concerned. Depending on the typology of the sub-project activities, the expected level of engagement, as well as the approaches and modalities may be defined into i) strategic engagement, awareness raising and public consultations (PC) to support CDPs and capacity building under technical assistance activities and ii) site-specific engagement for infrastructure investments both for rehabilitation and new construction.

Key areas where stakeholder engagement and outreach will be prioritized include:

- Promoting integrated, sustainable, and inclusive local tourism development through engaging stakeholders in:

- Participatory preparation of cluster concepts outlining the tourism vision;

- The development of CDPs;

- Refining/enhancing branding and promotion for target clusters;

- Technical assessments and pre-feasibility studies;

- Public-private engagement.

- Management of potential adverse impacts associated with the project’s activities. Such impacts may result from:

- Land acquisition and resettlement; economic displacement and impact on businesses;

- Community health and safety (H&S);

- Reduced access to water, natural resources, ecosystem services;

- Urban development;

- Increased traffic and tourism flows, new traffic patterns;

- Impacts on CH;

- Other environmental, social and CH impacts.

- Enhancement of potential development opportunities and social acceptance. The project may establish additional measures to enhance participation and access to benefits in terms of creating opportunities for women and vulnerable and marginalized groups, including but not limited to poor households, the elderly, and people with disabilities.

The above-mentioned objectives may be explored through meaningful stakeholder engagement which is a two-way communication with the focus on consultation, collaboration and empowerment of stakeholders. It includes:

- Informing - providing information with the use of bulletins, brochures, websites, social media, press releases, press conference;

- Consulting - gaining information and feedback for informed decisions with the use of surveys, focus groups, social media, online discussions, public meetings, forums, workshops, individual talks;

- Collaborating - working with stakeholders to understand their issues and concerns to jointly formulate responses with the use of forums, advisory panels, round table discussions, partnership;

- Empowering – delegating decision making on some issues to stakeholders through integration of stakeholders into governance structure as committee members (for instance in Grievance Redress Committee (GRC), Community Development Committee).

At the community level, stakeholder engagement can also be seen as a continuum of community involvement.

Figure 1 below, adopted from a diagram originally drawn by the International Association for Public Participation, and illustrates the levels of such a continuum.

| LEVELS OF COMMUNITY INVOLVEMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outreach Some community involvement Provide information to the community | Consult More community involvement Communication flows to the community and seeks feedback | Involve Better community involvement Communication flows both ways: participatory form of communication | Collaborate Community involvement Partnership with community on each aspect of the Project from development to solution | Share Responsibility Undertaking ownership and responsibility Establishment of the sense of ownership |

Figure 1 – Community Involvement Continuum

Based on the models discussed above, the project will adopt a tailored approach to stakeholder engagement that aligns with the needs and characteristics of each group. For vulnerable populations such as women, the elderly, persons with disabilities, displaced persons, and migrant workers, a more inclusive and participatory engagement model will be applied, ensuring their voices are heard and their needs addressed. For government entities, local authorities, and institutional stakeholders, a collaborative approach focusing on partnership and coordination would be most effective. This differentiated engagement strategy will help ensure that all groups are meaningfully involved in the project and that their contributions shape the project’s outcomes.

## Principles

To align with good practice approaches, the Project will apply the following principles for stakeholder engagement:

- Openness and life-cycle approach: Public consultations for the project/sub-projects will be arranged during the whole life cycle, carried out in an open manner, free of external manipulation, interference, coercion, or intimidation.

- Informed participation and feedback: Information will be provided to and widely distributed among all stakeholders in an appropriate format; opportunities are provided for communicating stakeholder feedback, and for analyzing and addressing comments and concerns.

- Inclusiveness and sensitivity: Stakeholder identification is conducted to enhance communication and foster effective relationships. The participation process for the project is inclusive, encouraging all stakeholders to engage in consultations at every stage. Equal access to information is ensured for all stakeholders, with sensitivity to their needs guiding the selection of engagement methods. Special attention is given to vulnerable groups that may risk exclusion from project benefits, such as families living under poverty line, women, the elderly, and persons with disabilities, displaced persons, migrant workers, as well as consideration of the cultural sensitivities of diverse ethnic groups.

- Flexibility: cultural context (for example, particular gender dynamics), or governance factors (for example, high risk of retaliation) inhibits traditional forms of face-to-face engagement, the methodology should adapt to other forms of engagement, including various forms of internet- or phone-based communication.

Figure 2 - Stakeholder Engagement Cycle

Figure 2 presents the stakeholder engagement cycle with its elements:

- Engagement and interaction with the stakeholders, initiation of a dialogue for collaboration;

- Identification of milestones for collaboration through a review of stakeholders’ interests and needs finding cross-cutting sections of mutual interest for profound collaboration;

- Collaboration and participation in Project activities to have a chance to pursue their own interest, to satisfy their needs, to influence on decision making processes;

- The engagement in participatory processes will allow them to express their feedback, to share responsibility for outcomes and to undertake the ownership of the results.

Stakeholder engagement is a continuous cycle that begins newly after reaching its endpoint. This process involves recording achievements, gathering feedback, enhancing performance, updating objectives, and initiating the cycle again at a higher level. This approach includes identifying and engaging new stakeholders while maintaining collaboration with committed existing partners.

The SEP will be updated with specific engagement approaches where CDPs are developed and/or site-specific investments become known, where they are not known these will be elaborated in a revised SEP during implementation.

## Limitations

Stakeholders are individuals or groups who have interest in or influence on the projects. The SEP aims to engage all stakeholders, or at least their respective groups, and to consider their needs and interests in the Project. However, managing stakeholder expectations and relationships can be challenging, especially when they have conflicting or competing interests, opinions, or demands.

Limitations to stakeholder engagement identified during the preparation stage may include the following:

- CDPs development:

- Exclusion of Affected Stakeholders: Affected stakeholders may be excluded from the inclusive development process due to their absence from the community or failure to properly engage with them.

- Reluctance to Participate: Some stakeholders may be unwilling to engage in the preparation of regional and tourism cluster development concepts and investment plans, often stemming from a lack of understanding of the project’s objectives and processes.

- Limited Skills and Experience: Certain stakeholders may lack the necessary skills and experience to effectively participate in these activities. Site-specific investments:

- Lack of a Systematic Approach: There may be a non-systematic approach to stakeholder engagement, which hinders the identification of stakeholders and the development and maintenance of constructive relationships, particularly with project-affected parties.

- Inadequate Assessment of Stakeholder Interest: A failure to assess the level of stakeholder interest and support for the project can prevent their views from being considered in project design and E&S performance.

- Incompetence or Indifference: There may be a lack of competence or indifference in promoting and facilitating effective and inclusive engagement with project-affected parties throughout the project life cycle. This includes not providing timely, understandable, accessible, and appropriately formatted information on project activities including E&S risks and impacts.

To address above-mentioned limitations in stakeholder engagement, the Project will follow a clear process for identifying and building relationships with stakeholders, particularly vulnerable and marginalized groups, as described in this SEP.

LWG will be formally established through the issuance of a Ministerial Decree by the MoE, at the community level by the municipality heads prior to project effectiveness. The composition, roles, responsibilities, and overall functions of the LWG are specified in Annex 5.

The LWG will comprise local representatives, including heads of communities, representatives from the municipality, representatives of local NGOs, nominated active residents and the private sector. The LWG will be engaged throughout the preparation of the CDPs under Component 1 as a consultative group to advise and guide the development of the CDPs, prioritize the interventions, and increase local ownership of the final CDPs developed. The LWG will also serve as the focal point for local communities to provide feedback or voice concerns regarding the preparation, technical design, and implementation of civil works under Component 2, as well as issues related to work quality in collaboration with ATDF, contractors, and other stakeholders. Additionally, the LWG will be responsible for regularly informing the community about the progress of activities within the clusters and managing grievances at the local level.

Stakeholder interests will be regularly assessed through focus groups, consultations and other methods, ensuring that proposed SE activities are targeted and adequate to the stakeholder needs and perspectives. Both project staff and stakeholders will be provided with training and workshop for effective engagement upon need. Project information regarding E&S risks will be properly disclosed in a timely and accessible manner, using various formats to reach diverse audiences. Established feedback and grievance redress mechanism (FGRM) will facilitate two-way communication, while collaboration with LSGBs and organizations will help bridge gaps in understanding and trust. Engagement strategies will be periodically assessed to allow for continuous improvement and responsiveness to stakeholder needs. Table 1 presents the proposed measures to address the SE limitations and challenges.

Table 1. Proposed Measures to Address SE Limitations

| SE Limitations and Challenges | Reasons for Limitations | Means to Address Limitations | Responsible Parties |
| --- | --- | --- | --- |
| CDPs Development |  |  |  |
| Exclusion of affected stakeholders | Absence from the community or failure to properly engage with them | - Project launch meetings will be held in all target regions to inform the communities on the Project and its components to initiate collaboration; - Round table discussions may follow to engage the key stakeholders in the dialogue and to receive their feedback; - Information about the preparation of the CDPs will be posted on the social media pages of the affected communities, enabling a wider range of community members and NGOs to get involved. This will encourage interested stakeholders to participate in the CDP preparation process at any stage, including during the draft CDP disclosure period. | TC, ATDF, Regional Administrations, LWGs, communities |
| Reluctance to participate | - Unwillingness to engage in the preparation of regional and tourism cluster development concepts and investment plans, - Lack of understanding of the project’s objectives and processes. | - Brochures or leaflets with the project key information will be prepared and disseminated in the target communities; - A local liaison officer will be engaged for each cluster to support the ATDF to ensure proper participation of the vulnerable groups in the PC and other group meetings. | ATDF, local liaison officers |
| Limited skills and experience | Lack the necessary skills and experience to effectively participate in CDPs preparation activities. | - Focus group discussions will be held targeting women, the youth and people with disabilities if needed; - Discussions on social media platforms will be initiated to generate opinions - Capacity-building workshops and training sessions will be organized to enhance the knowledge and skills of community members, ensuring meaningful participation | ATDF, local liaison officers, local authorities |
| Site-Specific Investments |  |  |  |
| Lack of a systematic approach | It can hinder the identification of stakeholders and the development and maintenance of constructive relationships, particularly with project-affected parties. | The systematic approach for SE will be applied in all target regions to identify stakeholders and develop constructive relations with them including: - Project launch meetings in all target regions; - Round table discussions; - Information about the Project will be available on social media pages of target communities; - Brochures or leaflets with the project key information will be prepared and disseminated in the target communities; - A local liaison officer will be engaged for each cluster to support the ATDF in relations with stakeholders. | ATDF, local liaison officers, local authorities, LWGs, consultants, contractors |
| Inadequate assessment of stakeholder Interest | A failure to assess the level of stakeholder interest and support for the project can prevent their views from being considered in project design and E&S performance. | - Stakeholder interest level will be periodically assessed through: - PC meetings; - Focus group discussions in target communities; - Discussion forums on social media platforms will be initiated to generate opinions. - Relevance of SEP actions will be periodically assessed and updated | ATDF, local liaison officers, local authorities, LWGs, consultants, contractors |
| Incompetence or indifference | There may be a lack of competence or indifference in promoting and facilitating effective and inclusive engagement with project-affected parties throughout the project life cycle. | Information on project activities including environmental and social risks and impacts will be provided to stakeholders in timely, understandable, accessible, and appropriate way through: - Disclosure of Environmental and Social Management Framework (ESMF), Resettlement Framework (RF), SEP; - Development and dissemination of brochures or leaflets with the project key information; - Qualitative interviews and focus group discussions, meaningful consultations; - Disclosure of Environmental and Social Management Plans (ESMPs), Environmental and Social Reviews (ESR), Cultural Heritage Management Plan (CHMP) for Dvin, Resettlement Plans (RP), if any, Labor Management Procedures (LMP) before the commencement of civil works; - Notification of communities on the start of the civil works | ATDF, local liaison officers, local authorities, LWGs, consultants, contractors |
| Lack of access or transportation | Living in remote areas, age or disabilities | - Ensure the dissemination of key project messages through multiple channels, including social media, web pages, banners, leaflets, word of mouth. - Deployment of local liaison officer to reach out remote communities or beneficiaries in person or by phone. | ATDF, local liaison officers, local authorities, LWGs, consultants, contractors |

# STAKEHOLDER IDENTIFICATION AND ANALYSIS

## Key definitions and main stakeholder groups

Project stakeholders are defined as individuals, formal or informal groups and organizations, and/or governmental entities whose interests or rights will be affected, directly or indirectly, by the Project, both positively and negatively, who may have an interest in Project implementation, and who have the potential to influence the Project outcomes in any way.

As per the WB’s ESMF, Environmental and Social Standard 10 (ESS10) on Stakeholder Engagement and Information Disclosure, stakeholders may be categorized into:

- Affected Parties – stakeholders that are affected or may be affected by the Project;

- Other Interested Parties – other parties who may have an interest in the Project.

As a special category of stakeholders, the SEP also identifies Disadvantaged or Vulnerable Groups, i.e., individuals or groups who may be more likely to be adversely affected by the project impacts and/or may require special engagement efforts due to their vulnerable status to ensure their equal representation in the consultation and decision-making process associated with the Project. Efforts will be made to identify vulnerable, disadvantaged, or marginalized groups and identify their specific needs.

Based on this categorization, the SEP outlines appropriate engagement mechanisms, their tentative timelines, roles and responsibilities for their implementation, and resources allocated for implementing the SEP activities. Stakeholder engagement mechanisms will be tailored to the needs of vulnerable groups as identified in the SEP.

GoA, Ministries State agencies, committees

Regional Governor Offices

PPPs

PAPs, tourists, local population, youth

REGIONAL LEVEL

NATIONAL LEVEL

COMMUNITY LEVEL

OTHER INTERESTED STAKEHOLDERS

POTENTIALLY AFFECTED STAKEHOLDERS

PARTNERS

PRIVATE SECTOR

Local authorities

SMEs owners

Vulnerable groups – women, children, people with disabilities, poor households, ethnic minorities, etc.

Local NGOs/CSOs

CSOs/NGOs

Media

Enterprises, companies, entrepreneurs

ATDF

DMOs

Academic research institutions

Local media

Figure 3 – Partners, potentially affected and other interested parties

## Potentially Affected Parties

Affected parties include local communities, community members, and other parties that may be subject to direct impacts from the Project.

CDPs preparation will involve broader stakeholders at all levels to ensure the key processes are inclusive and guided by good governance principles, including transparency, disclosure and stakeholder engagement and participation. The LWG will be engaged throughout the preparation of the CDPs under Component 1 as a consultative group to advise and guide the development of the CDPs, prioritize the interventions, and increase local ownership of the final CDPs developed.

Site-specific investments, such as civil works will need to be implemented with participation of host communities and understanding of impacts and mitigation measures will need to seek the views of project affected people, including vulnerable and marginalized groups. The LWG will also serve as the focal point for local communities to provide feedback or voice concerns regarding the preparation, technical design, and implementation of civil works under Component 2, as well as issues related to work quality in collaboration with ATDF, contractors, and other stakeholders.

The Project will positively impact stakeholders through capacity-building initiatives that provide training and career development opportunities to key staff in regional tourism companies and small local businesses. Additionally, institutional reforms will strengthen the MoE, the TC, the ATDF, and regional and local administrations. Affected communities, including vulnerable groups, will also gain improved access to jobs and services and will benefit from improved infrastructure, such as better access to public spaces and tourism sites, contributing to enhanced quality of life. Conversely, the project activities may adversely affect local small businesses or households, if due to resettlement impacts or E&S impacts during the construction stage. All those impacts will be mitigated according to RF and ESMF.

Broadly defined, affected parties may include the following stakeholder group specified in the above table.

Table 2. Key Affected Parties of the TRIP

| Stakeholder groups | Stakeholder interest | Engagement modes |
| --- | --- | --- |
| Potentially affected parties and beneficiaries |  |  |
| Local authorities: Hnaberd settlement of Artashat community (Dvin cluster in Ararat Region), Areni settlement of Areni community (Areni cluster in Vayots Dzor Region), Dilijan town (Dilijan cluster in Tavush Region), Yeghegis community (Yeghegis cluster in Vayots Dzor Region), Gyumri town (Gyumri cluster in Shirak Region), Goris community (Goris cluster in Syunik Region) and Jermuk community (Jermuk cluster in Vayots Dzor Region). | Will be engaged in working directly with the affected population, communicating the Project aim to the residents, organizing public hearings and information disclosure, gathering the residents’ concerns and suggestions as well as mitigating miscommunications. The affected settlements, as well as extended communities, are interested in the infrastructure development. The Project will contribute to social-economic and cultural development of affected settlements which will benefit on the whole and local SMEs especially from rehabilitation of basic infrastructure and services leading to improved access to tourism sites (access roads, parking, street lighting, etc.), improved street lighting and safety, and other public investments. Might be interested in receiving training and job opportunities related to the tourism industry. | Meetings, public consultations, workshops and presentations. |
| The local population: The residents of the settlements living in the neighborhood of the project affected areas. May be affected by the transportation of building materials, noise, vibration, air pollution and road safety issues or other construction-related impacts. | Interested in employment opportunities. Interested in benefiting from the economic opportunities that the project may bring to the communities. May be affected by impacts related to land use / access restrictions, temporary or permanent land acquisition / easement. | PCs, Focus group discussions; Disclosure of project documents (including ES documents); Mass media communication; Local liaison officer; Individual meetings |
| Tourists Tourist is a person who travels from a place of residence to a different town, city, county, and state for purposes of business, pleasure, recreation, education, arts, heritage, or culture. So, all the touristic sites should be attractive with appropriate infrastructure, green and ecofriendly to attract foreign as well as internal tourists. | Seek improved access to attractions and services, enhanced safety, and a better overall experience. Interested in eco-friendly tourism options and sustainable practices that minimize environmental impact. May be affected by the restricted access due to the Project. | Mass media Banners Disclosure of written information Warning signs and barriers |
| Youth | This group of stakeholders may benefit from improved connectivity and access to key attractions through green alternative modes (electric buses, cycling, etc.). | PCs Disclosure of written information |
| Small and medium enterprises (SME) located near/along the existing and connecting roads or the construction sites and their employees | May be affected by the access restrictions due to the Project works. Interested in raising revenues, increased procurement due to the Project activities. | PCs Individual meetings Disclosure of written information |
| Interested parties |  |  |
| MoE and TC | The MoE and TC are directly interested in the advancement of tourism infrastructure and preparation of CDPs and associated analytical studies under the GoA’s Cluster Approach. Interested in aligning CDPs (CDPs) with national and regional development strategies to enhance tourism. Interested in fostering community engagement and ownership in tourism initiatives. | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Ministry of Environment (MoEnv.): Environmental Impact Expert Examination Centre SNCO (State Non-commercial Organization) The Forest Committee and its “Hayantar” (ArmForest) SNCO | Ensures environmental protection and rational use of natural resources. The MoEnv, through its key departments, will have administrative authority over the project approval processes in compliance with environmental protection legislation. Is in charge of controlling the State Environmental Impact Assessment (EIA). | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Cadaster Committee | Maintains state registry of real estate, promotes the development and implementation of land policy. Cooperation with the Committee is important in relation to land acquisition. | Consultation meetings E-mails / Letters / Phone calls |
| Ministry of Education, Science, Culture and Sports | In charge of historical and cultural sites in Armenia. Interested in avoiding negative impacts on local historical and cultural sites. Interested in case of potential chance finds during the Project construction. | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Regional administrative offices (Marzpetarans) | Key stakeholder in terms of consultations on the measures to be implemented on the regional level. Interested in enhancing service delivery and infrastructure to improve the overall livability and attractiveness of the regions. Interested in institutional capacity building to effectively manage and promote local tourism offerings. | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Partners |  |  |
| Private Sector (Investors and Entrepreneurs) The list of private businesses to be engaged as stakeholders will be further developed during project implementation as specific interventions for each cluster are identified. | Aiming to participate in the development and promotion of tourism clusters for increased business opportunities. Interested in public-private engagement to enhance collaboration and investment in tourism initiatives. | Public consultations Focus group discussions Disclosure of project documents (including ES documents) Mass media communication Local liaison officer Individual meetings |

## Other Interested Parties

The projects’ stakeholders also include parties other than the directly affected parties (Table 3). These include:

- NGOs and CSOs as development partners

- DMOs

- Organizations involved in research and academia: Tourism faculties of different universities in Armenia and students of tourism schools.

- Local media illustrating the civil works and other activities implemented under the Project.

Table 3. Other Interested Parties of the TRIP

| Stakeholder groups | Interest | Engagement modes |
| --- | --- | --- |
| National NGOs: Armenian Women for Health and a Healthy Environment (AWHHE), Birds of Armenia (BoA) Project, Acopian Center for the Environment (ACE), CENN (Caucasus Environmental NGO Network) - Armenia office, Armenian Birdwatching Association, (AWP) WWF Armenia, ECOLUR Information Network, ICOMOS-Armenia, Hazarashen Armenian Center for Ethnological Studies (UNESCO accredited NGO), Armenian Architecture Research Foundation, Regional Center for Cultural Heritage, “Trails for Change” tourism NGO, Sustainable Tourism Development in Armenia NGO, and others. Regional and local NGOs and other civil society organizations, e.g.: Sisian Tourism Center; Sisian Women's Resource Centre Foundation; Kapan Women's Resource Centre NGO, Khustup environmental NGO, Ecological Safety and Democracy NGO, ECO SIS NGO; Kajaran Condominium for gender issues, “Guides from the South” Tourism Development NGO, Syunik Development NGO, Goris development center NGO, Sustainable development NGO, Shirak center NGO, Dilijan Youth Cooperation Center NGO, Shen NGO, Bridge of hope NGO, Arpa foundation | Consultations on specific topics, such as biodiversity, gender issues, or cultural heritage Iinterested in the information about the planned Project activities, its positive and negative impacts on the people and the environment. Close cooperation with NGOs will allow the Project to ensure smoother communication with the residents and organize more inclusive public hearings. | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Academia: School of tourism at Bryusov State University, school of service at Yerevan State University, Graduate certificate course in Tourism and Hospitality at the American University of Armenia (AUA) | This group can be supportive and have its valuable input in development of policy and reforms | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| DMOs The following private DMOs are currently operating within the designated priority clusters: 1. Goris Cluster - Syunik DMO. 2. Gyumri Cluster - Shirak DMO. 3. Dilijan Cluster- Go To Dili DMO in Tavush region. (No DMOs currently operate in Areni, Aparan, Yeghegis and Dvin Clusters) | This group can be highly interested in participation in this activity as the improved infrastructure can contribute to enhanced opportunities. | Workshops Public meetings Private meetings Disclosure of written information E-mails / Letters / Phone calls |
| Local media Ararat marz (Dvin cluster)- “Ararat”, “Artashat” newspapers. Shirak marz (Goris cluster)- “Gala”, “Shant”, “Tsayg” television channels, “Radio hay Gyumri” radio channel. Syunik marz (Goris cluster)- “Gorisi mamuli akumb”, “Gorisi yeritasardakan “Sharavigh” akumb, “Sisian info” web pages, “Ban and gorts”, “Zangezur”, “Vorotan”, “Syunyats yerkir” newspapers, “Zangezur”, “Syunik” TV channels. No local media in Vayots dzor and Tavush marzes (Areni, Yeghegis and Dilijan clusters). | Efficient collaboration with media may ensure broad public outreach on the Project. Local media are interested on the fresh materials for interviews and reportages. | Interviews Press releases Disclosure of written information E-mails / Letters / Phone calls |

## Disadvantaged and/or Vulnerable Groups

Within the Project, vulnerable and/or disadvantaged groups may include people who due to their circumstances may experience disproportionately adverse impacts from project activities and/or may face a higher risk of exclusion compared to other groups (Table 4).

These groups may include but are not limited to:

- People with disabilities

- Elderly, especially those living alone

- Women-headed households

- Families with many children

- Ethnic minorities

- Refugees

Table 4. Potentially vulnerable and marginalized groups

| Stakeholder group | Interest/vulnerability | Engagement modes |
| --- | --- | --- |
| Families registered as living below the poverty level, pensioners-headed households with no support, single-parent families, female headed households with no working adults, multi-children families, people with disabilities | May have difficulties to access or understand the information, provide feedback on the E&S aspects of the Project, or need specific assistance to assert their rights. May be interested in temporary employment opportunities. | Public meetings Special purpose events (meetings) Individual meetings Disclosure of written information Consultation support |
| Displaced people People from Nagorno Karabakh residing in the settlements that are close to the proposed project sites. | May experience heightened vulnerability due to displacement, loss of property or livelihoods, and lack of permanent housing or employment. May have limited access to information, documentation, and social services. Particularly interested in stable livelihood opportunities, community integration, and fair treatment in relation to project impacts and benefits. | Public meetings Special purpose events (meetings) Individual meetings Disclosure of written information Consultation support |
| Children living in the settlements close to the construction sites | May be exposed to risks related to traffic to/from the Project’s construction sites and need tailored information on road safety | Public meetings; Disclosure of written information; Warning signs and barriers |

Vulnerable groups within the communities affected by the Project may be identified, confirmed, and consulted through dedicated means, as appropriate. Approaches and/or representative organizations who can be engaged as partners to engage these groups will also be identified during the early stages of project implementation. The methods of engagement that will be employed by the project are outlined in the following sections.

To ensure participatory inclusion of women in discussing socioeconomic issues related to tourism development of their region/community, as well as to engage representatives of local business community dealing with tourism in identifying key obstacles and main directions of development of tourism-related sectors the engagement activities were conducted in the Project preparation period, which are described in the section 3.2.

## Modalities for Engagement

The TRIP relates to a large variety of stakeholders, ranging from ministries at the national level, to community and vulnerable groups. Engaging these actors helps to: 1) build a shared understanding and vision among all these key stakeholders; 2) understand capacity gaps and respond accordingly; and 3) coordinate all related initiatives and lead technical debates.

Mechanisms for stakeholder engagement across different groups are expected to include but not limited to PCs, interviews and focus groups discussions, including outreach to enable safe platforms to raise concerns.

The project will adopt a participatory approach from the outset, ensuring broad local involvement in the development of CDPs. Representatives from key tourism sectors, such as accommodation, catering, travel agencies, and transport services, will be engaged, with a focus on including women, youth, and family-owned businesses. Their insights, gathered through consultations, will inform tailored development strategies, ensuring relevance and effectiveness. Additionally, by documenting essential details like age, gender, specialization, and contact information, the project will foster ongoing connections with these stakeholders, encouraging their active participation in future activities and supporting professional networking within the local tourism ecosystem.

During the screening process the vulnerable groups of the affected communities will be identified, for instance women-headed households, ethnic minorities, persons with disabilities, extremely poor households, etc. These groups need meaningful consultation. Meaningful stakeholder engagement will focus on consultations, collaboration and empowerment of stakeholders, and two-way communication. Special information and communication materials will be prepared and disseminated among these groups. Focus group discussions, round table discussions, and separate meetings can be organized with the representatives of those groups or separate people to reveal their opinion about the project, their concerns and needs for inclusion in the Project. The concerns and suggestions should be considered during the elaboration of detailed designs as much as possible and feedback should be provided to the parties concerned.

Prior disclosure of relevant information in Armenian in a format accessible to target groups will be performed in advance of any public consultations, interviews and/or focus group discussions. This will also include disclosure of available FGRM channels. The feedback, opinions and suggestions received from the stakeholders will be taken into account and reflected in Project activities. They will be recorded by the FGRM, discussed and considered as much as possible even if they may result in the design modification.

Engagement associated with CDPs’ development will be integrated as part of public deliberation and consultation processes to solicit stakeholders’ feedback prior to their adoption.

The project will support the establishment of LWGs at the community level by the municipalities, comprising not just local representatives and heads of communities, but also local NGOs, nominated active residents, and the private sector. This platform will serve for women to actively participate and be represented. To increase the participation of women in decision making roles and ensure that their views are also considered in the CDPs, the LWGs will be comprised of at least 30 percent of women. The nature of LWG is to be engaged throughout the preparation of the CDPs as a consultative group to advise and guide the development of the CDPs, be the bridge between the community and contractors during the implementation phase. Thus, the inclusion of women in LWGs is not merely a matter of equity but also a strategic approach to enhancing the effectiveness and inclusiveness of community development efforts. Women participation brings diverse perspectives, addresses gender-specific concerns, enhances local ownership, empowers individuals, improves social cohesion, and ensures representation and advocacy.

Simultaneously, identifying local NGOs, particularly those involved in gender, social vulnerability, and youth issues, will be vital. Ideally led by women, these organizations can offer valuable perspectives on community challenges, facilitate focus group discussions, and ensure marginalized voices are heard. In areas lacking local NGOs, efforts will focus on engaging active women, youth, or regional NGOs with relevant experience. Their involvement will not only contribute to grassroots knowledge but also support the monitoring of the project’s social and gender impacts, ensuring that inclusivity remains a core principle throughout the initiative.

# STAKEHOLDER ENGAGEMENT ACTIVITIES AND INFORMATION DISCLOSURE DURING PROJECT IMPLEMENTATION

The project seeks to foster meaningful consultations with stakeholders identified above, particularly with those that may be adversely affected to ensure potential impacts can be avoided and/or mitigated through a participatory and inclusive process. The following outlines the engagement undertaken for preparation and activities planned to support Project implementation.

## Summary of Stakeholder Engagement during Preparation of the Stakeholder Engagement Plan

SEP will be biannually updated to reflect any modifications of the Project, as well as potential change in stakeholders and their interests and impacts. This SEP is developed in proportion to the nature and scale of the project, as well as its potential risks and impacts. The draft SEP was disclosed on the ATDF’s web site on October 10, 2024 in Armenian and English languages.

The first round of PC was held in February 2025 at the ATDF office in Yerevan, with participation from representatives of the TC, government agencies, regional administrations, NGOs, academia, and ATDF staff. E&S specialists introduced the TRIP and its E&S instruments — including the ESMF, SEP, RF, LMP and ESCP. A total of 17 participants attended, including 8 women. Participants discussed project objectives, cluster selection criteria, and integration of E&S requirements into subproject design and implementation. Key topics raised included beneficiary involvement, harmonizing with active initiatives in the target communities, mainly state-funded subvention projects, operation and maintenance of facilities, community capacity building, and the duration of the operational Project FGRM, and procedures for risk categorization.

The second round of PCs was organized between August and September 2025 in all target clusters — Dilijan, Dvin (Ararat), Jermuk/Areni/Yeghegis (Vayots Dzor), Goris, and Gyumri. A total of 139 participants (65 women) attended, representing community and regional administrations, CSOs, tourism sector representatives, and local residents. During the consultations the Project’s E&S instruments and the integration of E&S requirements into subproject design and implementation were discussed. The discussions also focused on cluster-specific issues, the establishment of LWGs, and other related topics. Following participants’ expressed interest in LWGs, an annex has been incorporated in the SEP outlining the procedure for establishing a Project Working Group, including eligibility criteria, participation mechanisms, and defined roles and responsibilities (See Annex 5). Minutes of all consultations are attached as Annex 6.

The project will undertake engagement activities over the course of its implementation. The detailed description of the planned SE activities is given in Annex 1.

During subproject preparation the PT at ATDF will further identify individuals or groups who may have different concerns and priorities about subproject impacts, mitigation mechanisms and benefits, and who may require different, or separate forms of engagement and various methods of communication.

## Information Disclosure

Stakeholders will be kept informed as the project develops, including reporting on project E&S performance and implementation of the SEP and FGRM, and on the project’s overall implementation progress.

The following principles will be applied when disclosing information on Project activities:

- The project will ensure that information to be disclosed is comprehensive and easily accessible and will be delivered to the stakeholders in a timely and quality manner,

- Information disclosure processes will be initiated at the very beginning of the Project and will be continued through the entire circle of the Project,

- Diverse information portals will be used for information disclosure including but not limited to the official websites, social media, news outlets, etc.

Preliminary strategy of information disclosure is presented in Table 5.

Table5. Preliminary Strategy of Information Disclosure

| Project stage | Target stakeholders | Information to be disclosed | Methods and timing proposed |
| --- | --- | --- | --- |
| Project preparation | - Communities and settlements - Private Sector (investors and entrepreneurs) - Regional administrative offices - Local and national NGOs - DMOs - Mass media | CDP | - Post on the ATDF and TC web page the Cluster brief information - Presentations for the local and regional stakeholders |
|  |  | Draft ESMF | - Posted on the ATDF web page on March 5, 2025. - PCs carried out on February 25, 2025 at the national level and during August–September 2025 at the local level. |
|  |  | Draft SEP | - Posted on the ATDF web page on October 18, 2024. |
|  |  | Draft RF | - Posted on the ATDF web page on October 30, 2024. - PCs carried out on February 25, 2025 at the national level and during August–September 2025 at the local level. |
|  |  | Draft ESCP | - Posted on the ATDF web page on March 06, 2025. - PCs carried out on February 25, 2025 at the national level and during August–September 2025 at the local level. |
|  |  | Draft LMP | - Posted on the ATDF web page on October 22, 2024. |
|  |  | Project Operational Manual (POM) | - Posted on the ATDF web page. |
| Subproject pre-design | Municipalities, CSOs, NGOs, and DMOs, private sector, local population | - Briefs on sub-projects - Presentation of FGRM | - Sharing an informative leaflet on project activities including description and activities of components and subcomponents, - Disclosed at TC and ATDF websites and the target communities websites, social networks - PCs |
| Design | Communities of the selected clusters, CSOs, NGOs and DMOs working in the selected regions, Project Affected Persons (PAPs), SMEs, local population, Environmental Impact Expertise Center (EIEC) | 1)draft Environmental and Social Impact Assessment (ESIA) in compliance with the RA EIAE Law, 2) draft ESMPs, ESR, and RPs approved by the WB 3) Presentation of FGRM 4) Disclosure of the updated SEP, final ESMPs, ESR and ESIAs 5) Disclosure of LMP 6) Disclosure of RPs, if any | - Disclosed at ATDF website and the affected communities’ websites, social networks during the design preparation period before the commencement of civil works - PCs on the E&S documents - Disclosure of ESIAs on the MoEnv website as part of the state expertise process. |
| Pre-construction | Communities of the selected clusters, CSOs, NGOs and DMOs working in the selected regions, PAPs, SMEs, local population | - Construction launch - Presentation of FGRM | - Construction launch meeting - Announcements on the web media - PCs |
| Construction | Communities of the selected clusters, PAPs, local population | - Construction progress - FGRM - Temporary outages of the utility (water, gas, electricity) related to construction works | - Web pages of ATDF and municipalities - Web media - Announcements on the information boards of the municipalities - Leaflets |
| Project closure and operation | MoE/TC, ATDF, Regional administrations, communities of the selected clusters, interested state agencies, CSOs, NGOs and DMOs working in the selected regions, public in general | Project completion report | - Disclosed at MoE and/or TC, ATDF websites and the target communities websites after completion of civil works |

## Resources and Responsibilities

### 3.3.1 Management functions and responsibilities

A high-level PSC will be established by Decree of the Prime Minister prior to effectiveness to provide overall oversight and inter-agency coordination of project implementation. The PSC will be chaired by the Deputy Prime Minister and will comprise representation from all the relevant stakeholders and institutions, including the MoE, Ministry of Territorial Administration and Infrastructure, Ministry of Education, Science, Culture and Sports, MoEnv, Minister of Finance, government agencies as Prime Minister’s office, Cadaster Committee, TC, Urban Development Committee, ATDF, and local and regional bodies, as may be needed.

The main purpose of the PSC is for strategic discussions regarding the Project, high-level decision making, including the approval of CDPs and subprojects, and facilitating inter-agency cooperation given the multi-sectoral nature of the project. The composition, representation and frequency of meeting of the PSC is elaborated in the POM.

The MoE will provide overall decision making and strategic leadership of the Project. The ATDF is the implementation agency (IA) which will form a PT including required specialists for successful implementation of the TRIP project. The ATDF will be responsible for implementation of this SEP.

The implementation of the SEP involves collaboration across multiple specialists to ensure that all aspects of the project SE are adequately addressed.

The ATDF Social Specialist will be tasked with overseeing the implementation of the SEP. This includes ensuring compliance with all activities and timelines as outlined in the SEP activities (Annex 1). Social Specialist will be responsible for updating, adopting, and executing the SEP, including the development of various engagement mechanisms for stakeholders and vulnerable groups.

The Social Specialist will coordinate with regional Community Liaison Officers (CLOs) and LWGs to ensure meaningful consultations and organize PC meetings. One CLO will be assigned to each selected cluster and should be appointed from within the respective LWG. The CLOs and LWGs will support the Social Specialist in conducting stakeholder engagement activities in the regions, identifying target and vulnerable groups, organizing consultations, and acting as FGRM focal points.

Other specialists involved in SEP implementation will include Environmental Specialist, M&E specialist and technical specialists. The Environmental Specialist will assist the Social Specialist in organizing and conducting PCs, where both E&S concerns can be addressed simultaneously. The M&E Specialist will support the Social Specialist by designing and implementing a monitoring framework to track the outcomes and impacts of the SE activities. The M&E Specialist will contribute to regular reporting on SEP activities, highlighting areas where engagement is succeeding and identifying areas for improvement. Technical Specialists (engineers, supervisors) will help explain technical aspects of the project to stakeholders during consultations, ensuring that communities understand how the project may affect their environment and social life.

### 3.3.2 Resources

The resource requirements for SEP implementation are generally allocated to key areas such as staffing, communication campaigns, capacity building, FGRM implementation, and other essential activities to ensure effective SE and project communication. SEP budget is presented in Annex 4.

# FEEDBACK and Grievance Redress Mechanism

## Introduction to Feedback and Grievance Redress Mechanism

The Project FGRM provides a transparent and credible process for achieving fair, effective and lasting outcomes. It also serves to build trust and cooperation as an integral component of broader community engagement, helping to identify issues early and facilitate timely corrective actions.

The FGRM addresses grievances that arise in the Project by affected communities and external stakeholders under all components either due to actions by the ATDF or the consultants and contractor/sub-contractors contracted by the ATDF. A separate mechanism is developed to address worker grievances, described in the Project LMP. The ATDF is responsible for managing the FGRM; however grievances on the Project will likely relate to the actions of the Contractors and Consultants and therefore will need to be resolved at the local level. The ATDF with the support of the Design Consultant, Construction Contractor and/or Technical Supervision Consultant will administer the FGRM process at the local level deciding the best course of action to resolve the grievance.

The Project FGRM also deals with resettlement issues: land and other assets acquisition (e.g., amount of compensation, suitability of residual land plots, loss of access roads and business, etc.) as well as the losses and damage caused by construction and /or rehabilitation works. Therefore, the FGRM is described also in the RF in detail.

The FGRM is an instrument with which:

- Affected people can make a complaint or resolve any dispute that may arise during the course of the implementation of the Project;

- The ATDF ensures that appropriate and mutually acceptable redress actions are identified and implemented to the satisfaction of complainants;

- The ATDF supports accessibility and transparency in handling complaints and grievances;

- The ATDF manages time factor (avoids the need to resort to judicial proceedings, where possible).

Typical grievances under Component 2 may relate to:

- Land acquisition and physical displacement;

- Damages due to civil work;

- Environmental impacts; and

- Direct and/or indirect social - economic impacts.

FGRM will include the following Steps:

- Step 1, grievances may be submitted at any time during project implementation through various channels, including written submissions, telephone hotline or mobile phone, email, social media such as the Facebook page, the website, or through grievance logbooks available in the community and at construction sites. Anonymous grievances will be accepted and addressed.

- Step 2, all grievances are registered in the FGRM log using a standard form. They are then classified according to the category of the complaint, such as technical, social, environmental, or health and safety issues. Registration and initial acknowledgment to the complainant will be completed within two working days of receipt.

- Step 3 involves resolution at the local level (Stage 1). The designated FGRM focal point in the community or the contractor’s site-level FGRM focal point will handle the complaint, aiming to resolve it on the spot whenever possible. If the grievance requires further investigation, the PAP will be informed and the case will remain active. The PAP also has the right to bypass Stage 1 and proceed directly to Step 4. Local resolution must be completed within seven calendar days of receipt. If unresolved, the complaint will be referred to the next stage no later than the seventh day.

- Step 4 (Stage 2), unresolved grievances are reviewed at the Project level by the ATDF. The community FGRM focal point assists the PAP in lodging a formal written complaint. The ATDF FGRM Coordinator reviews the complaint and refers it to the relevant department for redress within ten calendar days of receipt. The final written decision must be provided to the complainant within thirty calendar days of receipt.

- Step 5 allows for escalation if the complainant is dissatisfied with the Stage 2 decision. The complainant may take the case to the courts of the Republic of Armenia (RoA).

The overall timeframes for the process are as follows:

- submission of grievance – any time;

- registration and initial acknowledgment – within two working days;

- local resolution – within seven calendar days;

- referral to ATDF – within ten calendar days;

- final decision at ATDF – within thirty calendar days;

- escalation – according to national or international procedures.

## Grievance Records and Documentation

The ATDF social specialist assigned to the Project will act as an FGRM Focal Point to manage a grievance log to keep a record of all grievances received. The log contains the name of the individual or organization lodging a grievance; the date and nature of the grievance; any follow-up actions taken; the solutions and corrective actions implemented by the Contractor or other relevant party; the final result or status of the grievance (see Annex 3).

The Supervisor and construction companies in their monthly monitoring reports will provide information on grievance management. Grievance monitoring and reporting will occur in the ATDF’s semiannual and annual progress reports to be prepared for the WB.

Information on the Project and FGRM will be available on the ATDF’s website and will be posted on information boards in affected communities in the Project area (see Annex 2, the form for the FGRM focal points contact information). Information can also be obtained from the FGRM Focal Point. The FGRM mechanism will not impede access to the Country’s judicial or administrative remedies.

## 4.3 Closure of Grievances

A grievance will be considered “resolved” or “closed” when a resolution satisfactory to both parties has been reached, and after corrective measures has been successfully implemented. When a proposed solution is agreed between the Project and the complainant, the time needed to implement it will depend on the nature of the solution. However, the actions to implement this solution will be undertaken within one month of the grievance being logged and will be tracked until completion. Once the solution is being implemented or is implemented to the satisfaction of the complainant, the status of the complaint in the FGRM log will be marked as “Closed”. The FGRM log will be submitted to the WB team.

In certain situations, however, the Project may “close” a grievance even if the complainant is not satisfied with the outcome. This could be the case, for example, if the complaint refers to the technical solutions of the design and it cannot be modified, or the grievance has no justification and contains incorrect information or data. In such situations, the Project’s efforts to investigate the grievance and to arrive at a conclusion to reject the complaint.The status of the grievance in this case will be “Rejected”. The complainant will be notified about the decision within a month from the date of the grievance record.

A grievance may be also classified as “Closed – Not Resolved” when the FGRM process at all applicable stages has been completed in accordance with the established procedures and timeframes, but no mutually acceptable resolution has been reached. This classification may occur in situations where:

- The complainant rejects the final proposed resolution but chooses not to pursue further escalation through judicial or higher-level mechanisms (e.g., WB grievance channels).

- The complainant cannot be reached despite reasonable and documented efforts (multiple contact attempts using available channels, including written notifications).

- The grievance falls outside the scope of the Project or FGRM mandate, and the complainant has been duly informed in writing, with referral information provided for the appropriate authority.

- The complainant explicitly withdraws the grievance before resolution is reached.

In such cases, the grievance record will be marked as “Closed – Not resolved” in the FGRM log, including a clear explanation of the circumstances, actions taken, dates, and all correspondence or contact attempts. This status confirms that the Project has fulfilled its procedural obligations, even though the substantive issue remains unresolved from the complainant’s perspective.

The FGRM chart with the two stages is presented below.

Figure 4. FGRM Chart

## 4.4 Communicating FGRM to the Project Stakeholders

The ATDF through the E&S team will establish a first step of grievance redress mechanism at the local level in cooperation with local authorities and LWGs, in order to provide a direct channel to the affected persons and community members for voicing any grievances with the Project. The contact information and mechanism to submit verbal or written grievances will be publicized extensively among the local community (for example, through visible boards, complaints boxes, information boards in public offices, during project consultations, etc.). Contact information such as name, telephone, email of local focal point for grievances will be clearly stated. The ATDF is responsible for verifying that local grievance redress mechanisms are present and properly advertised. It is also the ATDF’s responsibility to monitor that grievances are properly recorded at the local level.

Grievances will be resolved at the local level, where possible. Where this is not possible, they will be forwarded to the FGRM Focal point in the Project level (Social specialist of the Project). Grievances and their resolution will be recorded and redressed in an appropriate time frame of no more than 30 days.

## 4.5 Sexual Exploitation and Abuse and Sexual Harassment Grievances

The SEP establishes sensitive procedures related to grievances concerning Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH) (SEA/SH), ensuring a survivor-centered approach.

All complaints, especially SEA/SH-related, will be treated with strict confidentiality. The identity of the survivor will be protected at all stages. The procedure will follow a survivor-centered approach, prioritizing the survivor’s needs, consent, and preferences. To ensure timely and survivor-centered support, ATDF will utilize and maintain an updated mapping of local service providers capable of delivering psychosocial, medical, and legal assistance to SEA/SH survivors. The mapping process will be coordinated by the ATDF Social Specialist in collaboration with Local LSGBs and relevant national institutions. Information on the contact details and geographic coverage of NGOs providing specialized care in Armenia is available through the national service platform. In addition, the mapping of location-specific service providers—including regional health centers for emergency medical and reproductive health services, local psychologists, counselors, or NGOs for psychosocial support, and legal aid organizations or bar associations for legal counseling and representation—will be incorporated into the subproject site specific SEPs. .

Confidential data management is central to the integrity of SEA/SH response. All grievances or reports related to SEA/SH will be handled in a confidential manner that respects the survivor’s privacy, consent, and dignity. Only designated and trained personnel, namely, the social specialist at ATDF, the contractor’s FGRM focal point, and the community FGRM focal point, will have access to case-related information. Data collection will be strictly limited to non-identifying details, including the date, type of incident, type of support provided, and follow-up status. Survivor names, locations, or other personally identifying information will not be recorded in any database or report. All written records will be stored in password-protected electronic files with restricted access. Statistical summaries (e.g., number of cases reported, type of services provided, and resolution time) will be aggregated and anonymized before inclusion in periodic reports to the WB or other stakeholders.

SEA/SH grievances will be prioritized and resolved within a clearly defined timeframe, typically within 30 days or sooner, depending on the severity of the case. The survivor will be regularly updated on the progress of the grievance resolution process, ensuring transparency and trust in the procedure.

Details on addressing grievances related to workplace concerns, including those involving SEA/SH, are provided in the Project LMP.

## Grievance Resolution

The GRC at Project level will be established to address complaints and grievances pertaining to resettlement and to pre-empt all disagreements being referred to the court. The GRC will include ATDF staff, and representatives of the relevant state authorities and/or Marzpetaran in the Project area, and communities affected by the components of the TRIP Project. The composition of the GRC will be shared with the WB team prior to commencement of RP preparation and of any construction work under the Project. The GRC will be convened by the ATDF on a case-by-case basis, to address complaints and grievances pertaining to resettlement.

The Project-level GRC procedure must ensure maximum access, transparency, disclosure and participation and will be aimed at maximum protection of interests of affected population.

The GM for workers is described in  in LMP prepared for the Project.

## ANNEX 1. PLANNED STAKEHOLDER ENGAGEMENT ACTIVITIES

| Project Activities | Stakeholder engagement method | Target Stakeholders | Objective of stakeholder engagement activity | Topic of consultation / message | Responsibilities |
| --- | --- | --- | --- | --- | --- |
| Component 1. Fostering Integrated and Sustainable Cluster Development Subcomponent 1.1: Development of CDPs |  |  |  |  |  |
| - Development of CDPs | - Regional round table workshop - Working group discussions - Forums on social media - Public meetings | MoE, MoESCS, MoTAI, MoEnv, TC, ATDF, regional administrations of Ararat, Aragatsotn, Shirak, Syunik, Tavush and Vayots Dzor, DMOs, CSOs, NGOs, private sector | - Ensuring participatory preparation of cluster concepts, public awareness campaigns and associated citizen engagement activities during and after the development of CDPs to ensure local ownership and informed decision-making. | - Cluster concept - Presentation of draft CDPs - Consideration of feedback and suggestions | TC and ATDF through TA Consultants |
| - Presentation and disclosure of draft and final CDPs | - Regional round table workshop - Forums on social media - Public meetings - Websites (ATDF, MOE, local communities, regional administrations) | MoE, MoESCS, MoTAI, MoEnv, TC, ATDF, regional administrations of Ararat, Aragatsotn, Shirak, Syunik, Tavush and Vayots Dzor, DMOs, CSOs, NGOs, private sector | - Enabling key stakeholders to provide their opinion, feedback, suggestions on the draft CDPs - Integrating and addressing raised suggestions, opinions and considerations | The content of CDPs | TC will coordinate presentation of the CDPs, ATDF will coordinate disclosure of draft and CDPs on social media and websites, including regional administrations and local communities |
| - Provision of trainings, tools, vocational education | - Information on trainings and vocational education will be sent by email list - Announcement on trainings will be placed on social media sites of the target communities | DMOs, CSOs and regional tourism organizations | - Technical support for branding, marketing, and promotion activities within the tourism value chain, - Development and implementation of site management plans to enable sustainable operations and maintenance of touristic products - Information, data collection and reporting of local tourism statistics | - Branding, - Marketing, - Promotion activities, - Site management plans development and implementation, Data collection and reporting | TC and ATDF through TA Consultant |
| - Establishment, management, and operations of DMOs | - Round table discussions with participation of established DMOs’ representatives | CSOs, NGOs, tourism organizations potentially interested in destination marketing | - Supporting better local tourism management | Role of DMO in regional tourism development | TC and ATDF through TA Consultant |
| Component 2. Supporting Climate-Resilient Infrastructure and Promoting Private Sector Participation in Local Economies Sub-component 2.1 Rehabilitating and Upgrading Infrastructure and Services |  |  |  |  |  |
| - Elaboration of designs for subprojects (including development of ESIAs, ESRs, ESMPs, CHMP, RPs if any, FGRM, and update of SEP) | - PC meetings to present draft ESMPs, ESIAs, ESRs, CH and RPs - Meaningful consultations with PAPs - Separate meetings for women and vulnerable groups; - Social Media - Facebook, WhatsApp; - Disclosure of documents on the official websites - Dissemination of written information - brochures, posters, flyers, website | - The affected communities: Hnaberd settlement of Artashat community (Dvin cluster in Ararat Region), Areni settlement of Areni community (Areni cluster in Vayots Dzor Region), Dilijan town (Dilijan cluster in Tavush Region), Yeghegis community (Yeghegis cluster in Vayots Dzor Region), Gyumri town (Gyumri cluster in Shirak Region), Goris town (Goris cluster in Syunik Region), Jermuk town (Jermuk cluster in Vayots Dzor Region) - People affected by land acquisition and resettlement; - SMEs; - People residing in project area; - Vulnerable households | - Enabling key stakeholders to provide their opinion, feedback, suggestions on E&S impacts and suggested mitigation measures - Integrating and addressing raised suggestions, opinions and considerations | Disclosure of draft - RPs, - ESIA reports - Site Specific ESMPs, ESRs, CHMP Providing information about FGRM | ATDF, design company, ESIA and RAP Consultants |
| - Civil works | - Public notification meetings, - Info boards, - Dissemination of written information - brochures, posters, flyers, website | - Affected communities; - PAPs (if any); - SMEs located nearby; - People residing in project area; - Vulnerable households to be aware of temporal employment opportunities | - Raising awareness of the affected stakeholders on the construction activities - Encouraging affected and beneficiary communities to take responsibility and develop sense of ownership for improved infrastructures | - Construction activities - Environmental, Social, Health and Safety (ESHS) - FGRM | Project Manager, Project Coordinator, E&S team, Contractor, Technical Supervision Consultant |
| - Operation | - Public notification meetings, - Mass media - Info boards, - Private meeting | - Affected communities; - PAPs (if any); - Tourists - Entrepreneurs and businesses | - Raising awareness on the new destinations and tourism infrastructures developed under the project - Monitoring of the livelihood restoration process of affected PAPs | - New destinations and tourism infrastructures - New investment and business opportunities - Livelihood restoration of the PAPs | MoE DMOs ATDF External monitoring consultant |
| Component 2: Supporting Climate-Resilient Infrastructure and Promoting Private Sector Participation in Local Economies Subcomponent 2.2: Fostering Private Sector Participation, Enhancing Professional Skills, and Enabling Job Creation |  |  |  |  |  |
| - Public private investments and enabling PPPs, | - Information on partnership possibilities will be sent by the contact information available at MoE - Round table discussions | - Private sector, potential investors | - Development of PPPs | - PPPs | MoE, TC and ATDF, LSGBs, Consultant, Liaison Officers |
| - Incremental financial support for business development (e.g., matching grants) | - Announcements publicized at the TC, ATDF, LSGBs’ websites, - Announcements placed on social media sites of the target communities | - Regional tourism organizations in target regions, - DMOs | - Provision of matching grants | - Possibility for business development | TC and ATDF, LSGBs, Consultant, Liaison Officers |
| - Provision of professional skills development | - Announcement on trainings will be placed on social media sites of the target communities, - Meaningful consultation will be provided to vulnerable and disadvantaged groups, - Informative leaflets will be disseminated in the target communities and settlements | - SMEs, local communities, and tourism workers - Priority will be given to disadvantaged communities and groups (e.g., women, youth, and vulnerable groups) | - Upgrading professional skills and knowledge | - Possibility to develop professional skills | TC and ATDF through TA Consultant, Liaison Officers |

## ANNEX 2. THE FGRM FOCAL POINTS AND THE FGRM COORDINATOR’S CONTACT INFORMATION PUBLICATION FORM

| Description | Contact Details |
| --- | --- |
| FGRM focal point at community level |  |
| FGRM Coordinator |  |
| To: |  |
| Address: |  |
| E-mail: |  |
| Website: |  |
| Telephone: |  |

## ANNEX 3. THE GRIEVANCE REGISTRATION LOG

| No. | Name /Surname | Submission Channel | Complainant Status | Date (dd/mm/yy) | Subject | Description of the Grievance | Entities/ ATDF Departments Involved | Follow-up Actions Taken | Current Status | Closure Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## ANNEX 4. SEP BUDGET

| Budget categories | Quantity | Unit cost per year, $ | Total costs, $ | Remarks |
| --- | --- | --- | --- | --- |
| - Service contracts |
| CLOs in Municipalities | 7 | 1,000 | 7,000 | 1 in each Marz. CLOs will be hired before sub-project preparation activities start in each community and will be maintained till completion of construction works. |
| - Events |
| Training on the ES Project documents (SEP, RF, ESMF, LMP, ESCP) for the municipalities and NGOs | 7 | 0 | 0 |  |
| PC on the sub-project related ES documents (ESIA, ESMP, SEP, LMP) | 28 | 0 | 0 |  |
| Construction launch meeting | 10 | 600 | 6,000 |  |
| Training on environmental, social issues for Contractor /Consultant staff | 10 | 500 | 5,000 |  |
| 3. Paper based products |
| Informative leaflets on the Project (two sided) | 200 | 0.6 | 120 |  |
| Brief informative leaflets on the Clusters (two sided) | 200 | 0.6 | 120 |  |
| TOTAL STAKEHOLDER ENGAGEMENT BUDGET |  |  | 18,240 |  |

## Annex 5. INSTITUTIONAL ARRANGEMENTS FOR THE LOCAL WORKING GROUP (Subject to revision after the Project Operational Manual approval)

The LWG is established by the decision of the head of the community where the subproject is being implemented, with the consent of PWG.

All LWGs shall be formally established and operational prior to the initiation of any subproject activities. The establishment of LWGs will be a prerequisite for subproject commencement and will ensure that local-level coordination, stakeholder engagement, information sharing, and Feedback and grievance redress mechanisms are in place from the outset of implementation.

The LWG may include the following members:

- Community head (Mayor);

- Deputy community head or community development officer;

- Community engineer/construction specialist (if available);

- Community environmental officer (or an employee performing similar functions);

- Social affairs officer or community social worker;

- Secretary;

- Representatives of local NGOs or beneficiaries;

- Representatives of the private sector (in an advisory capacity;

- Local focal points of contractor and supplier companies (upon need).

To promote inclusiveness and gender equality in local decision-making, women’s representation in LWGs will be ensured throughout the Project. At least 30 percent of LWG members shall be women. This requirement will be applied during the establishment and any subsequent reconstitution of LWGs. Compliance with this requirement will be monitored by ATDF as part of overall reporting arrangements.

Main Functions of the LWG are:

- Support and coordinate subproject/s implementation at the local level.

- Active participation during the development of CDPs and submission of necessary approvals to the community council.

- Collection and transmission of data, documents, and information required for project implementation to the PWG and the ATDF.

- Support in obtaining permits, resolving issues and obstacles within the community’s area of responsibility, and ensuring timely implementation of project activities.

- Ensuring communication about the Project with beneficiaries, local population, and community structures.

- Discussion of locally emerging issues and challenges, proposing realistic solutions, and submitting them to the responsible project authorities in close coordination with the relevant ATDF staff.

- Verification of processes related to land use, existing infrastructure conditions, and other procedures — in line with the Project’s requirements, procedures, and timelines in the frames of WB respective guidelines and coordination of respective ATDF staff.

The LWG is responsible for:

- Implementing support measures to ensure transparent and efficient progress of project works at the local level.

- Providing information to the PWG and the ATDF in a timely manner, in accordance with the requirements.

- Recording and forwarding community members’ and beneficiaries’ questions, complaints, and suggestions to the responsible authorities and ATDF according to the Project Feedback and Grievance Redress Mechanism (FGRM).

- Organizing internal coordination and problem-solving related to project processes within the community and local structures, as well as facilitating mutual agreements with the residents for the purpose of project interventions and implementation in line with the WB respective guidelines and coordination of respective ATDF staff.

LWG meetings are held as needed, but not less than once per quarter per annum. Meetings are considered valid if at least half of the members are present. Decisions are made by open vote and adopted by a simple majority of those present. Minutes of each meeting are prepared, signed by the members of the LWG, and submitted to the PWG and ATDF.

The LWG must regularly submit reports on the works carried out at the local level, in accordance with formats and request defined by the PWG. The activities of the LWG are subject to monitoring by the ATDF.

The Secretary of the LWG is appointed by the decision of the community head and performs the following functions:

- Preparation and organization of LWG meetings and sending invitations to members.

- Preparation of meeting agendas in coordination with the Chairperson.

- Recording discussions and decisions during the meetings.

- Drafting, signing, and maintaining minutes and decisions.

- Providing copies of minutes and decisions to the PWG.

- Collecting data, documents, and proposals received from the community and beneficiaries.

- Maintaining communication among LWG members, and between the community and the PWG.

- Organizing communication with beneficiaries and ensuring information dissemination to the local population.

## ANNEX 6. MINUTES OF PUBLIC CONSULTATIONS MEETING ON ENVIRONMENTAL AND SOCIAL INSTRUMENTS FOR ARMENIA TOURISM AND REGIONAL INFRASTRUCTURE PROJECT

Minutes of the Public Consultation for the State Agencies and Reginal Administrations

(1st round)

The consultation meeting on the E&S Instruments for the TRIP was organized by the ATDF in collaboration with the TC. The meeting aimed to ensure transparency and inclusiveness in the preparation of E&S instruments by engaging key stakeholders in an open dialogue.

The consultation served as a platform for representatives of government institutions, regional administrations, NGOs, academic institutions, and other interested parties to review and discuss the draft E&S documents developed for TRIP in accordance with the WB ESF and national legislation.

During the meeting, participants were presented with the project objectives, components, and proposed approaches for managing E&S risks and impacts. Constructive feedback and recommendations were collected to strengthen the quality, applicability, and ownership of the E&S instruments, ensuring their effective integration into project implementation and future regional development initiatives. The E&S instruments along with the invitations to participate in the meeting were distributed to the respective organizations in advance. The details of the PC held are presented below.

Date: February 25, 2025

Time: 14:00 (Yerevan time)

Venue: ATDF Office, Yerevan, 31/1 Ulnetsi Street

Participants: Government agencies, regional administrations, NGOs, academic schools, ATDF staff.

Total number of participants was 17, of which 8 women and 9 men.

Agenda:

- Welcome and Opening Remarks

- Presentation of TRIP

- Presentation of E&S Instruments

- Stakeholder Feedback and Discussion

- Next Steps and Closing Remarks

- Welcome and Opening Remarks

The meeting commenced with a welcome by ATDF E&S department head Mrs. Grigoryan, who highlighted the objectives of the consultation, emphasizing transparency, stakeholder engagement, and the importance of incorporating feedback into the E&S instruments of the project. She also presented the ESCP that will be a part of the Loan Agreement between the WB and the Government of the RA.

- Presentation of the Project

Mrs. Anahit Voskanyan, the representative of the TC, presented the objectives and components of the project. She informed the participants about the criteria for selecting the clusters and explained the process of developing CDP. She also mentioned that the draft CDPs will be shared with the administrations and communities of the target regions for feedback and suggestions. Additionally, she highlighted that the TC will hold meetings in the regions to conclude the previous LEID project and launch the TRIP.

- Presentation of E&S Instruments

Mrs. Vardanyan, social specialist of ATDF and Mrs. Gabrielyan, environmental specialist of ATDF provided an overview of the E&S documents, including the ESMF, SEP, RF, LMP, Environmental and Social Commitment Plan (ESCP). The presentation covered key environmental and social risks, proposed mitigation measures, stakeholders identification, engagement activities and methods, resettlement risks and impacts, entitlements and eligibilities of affected persons as well as labor related  H&S risks and proposed measures to eliminate or minimize the risks, integration of E&S documents in bidding packages, supervision and monitoring of the project operations and activities in  compliance with WB E&S Standards and state Laws.

- Stakeholder Feedback and Discussion

Stakeholders were invited to share their comments, concerns, and recommendations. The following key points were raised:

Questions:

- Since SMEs are also considered beneficiaries, how exactly are they affected and what will be the benefit? (Syunik marzpetaran representative)

- Private investment programs are planned to be implemented. It would benefit business promotion. Small and medium-sized enterprises can benefit as well from increased tourist flows and reconstructed and restored infrastructures will contribute to the formation of favorable conditions for local business development. (ATDF)

- Is it possible to consider combining similar programs with community subsidy programs? (Tavush marzpetaran representative)

- All subsidy-eligible programs are reviewed by the TC; however, there have been no overlaps with the programs implemented or planned so far.(TC)

- The community presents a 5-year development plan, and is there a line in that plan dedicated to the maintenance of the facility that has just been commissioned? (WWF Armenia representative)

- Operation and Maintenance plans will be developed along with the sub projects, which will be approved by ATDF and signed by the municipality before the start of construction works. This will help the respective municipalities contribute to the sustainable results of the project with budget and capacity planning.(ATDF)

- Is there a block for community capacity development, for example, training, etc. (WWF Armenia representative)

- The program includes a soft component with extensive training sessions, within which the issue raised will be considered.(TC)

- How long does FGRM last? I mean, what solutions are given to the problems that arise after about 3 years of commissioning, and by what mechanism, who should be contacted then?

- During the defect liability period after the rehabilitation and/or construction of infrastructures the grievances related to the construction quality can still be sent to the ATDF. However, after about 3 years of commissioning grievances can be sent through hot lines of marzpetarans, communities and related ministries.(ATDF)

- With whom is the coordination carried out regarding the selection of the area for the Dilijan cluster?

- Concept for Dilijan cluster is under development, and consultants have been hired. Site studies and research have been conducted, and based on the data, sites have been selected by a consulting organization. As part of the studies, focus group discussions and consultations with stakeholders and beneficiaries are planned for implementation.(TC)

- Is there any categorization of impacts of the sub projects?

- Risk classification will be carried out in accordance with the WB’s ESF guidelines. An E&S screening will be conducted to determine the required level of assessment. Activities will be categorized into four risk levels: High, Substantial, Moderate, and Low. The description of each category and the process of categorization are detailed presented in the ESMF.(ATDF)

- How will air pollution be measured?

- Air pollution will be measured in case of complaints. In such cases, the Contractor will conduct particulate matter (PM) measurements (ATDF).

Participants’ suggestions for improvement of the documents and procedures:

- In the documents, the words "Real estate appraisal activities" should be replaced with the words "Appraisal activities", as well as the law has entered into force on July 1, 2022 and it  applies to real estate and movable property valuation activities, while previously it only applied to real estate valuation activities. (representative of RoA Cadaster Committee).

- The respective corrections were done.

- Closer collaboration with regional administrations at design phase. (representative of Ararat marzpetaran).

- Regional administrations have been identified as stakeholders and their Involvement has commenced from this meeting and close collaboration is anticipated. In particular there will be launch meetings in regions during which the sub projects will be presented. The sub projects can be approved by the Community councils with all the requirements and maintenance obligations. (representative of Vayots Dzor marzpetaran).

- The sub-projects will be better grounded if they are approved by community councils.

- It can be considered.

- The defect liability period after commissioning can be extended for about 2-3 years, since 1 year is not enough (representative of National University of Construction and Architecture).

- This suggestion will be considered during the development of the POM.

- Next Steps and Closing Remarks

  - Stakeholders were informed that their feedback will be reviewed and integrated into the final E&S instruments where applicable.

  - The revised documents will be shared with stakeholders for further input.

  - The consultation process will continue through project launch meetings in regions and PC meetings in communities, discussions in affected settlements and meaningful consultations with vulnerable groups.

The meeting concluded with closing remarks from Mrs. Grigoryan thanking all participants for their valuable contributions and reaffirming the commitment to addressing ES concerns responsibly.

Minutes of the Public Consultation held in the Cluster Locations

(2nd round)

Below are presented dates, locations and the number of participants of the PCs.

| Location | Date & Time | Total Number of Participants | Number of Women Participants | Participation by target groups |
| --- | --- | --- | --- | --- |
| Dilijan Municipality (Dilijan Cluster) | August 22, 11:30 | 16 | 6 | Community administrations, CSOs, local residents |
| Ararat Regional Administration (Dvin Cluster) | August 26, 10:00 | 22 | 14 | Community administrations, Regional administrations, Tourism sector |
| Vayots Dzor Regional Administration (Jermuk, Areni and Yeghegis Clusters) | August 27, 14:00 | 48 | 12 | Community administrations, Regional administrations, CSOs, DMO, Tourism sector, Residents |
| Goris Municipality (Goris Cluster) | August 28, 11:00 | 33 | 23 | Community administrations, CSO, DMO, Tourism sector, Local residents |
| Shirak Regional Administration (Gyumri Cluster) | September 8, 11:00 | 20 | 10 | Community administrations , Regional administrations, CSOs, Tourism sector, local residents |

The announcement of the PCs was published on the official website of the ATDF (www.atdf.am) on August 8, 2025, as well as was sent to the regional administrations of Ararat, Shirak, Vayots Dzor Marzes and the administrations of Dilijan and Goris communities in official letters. These institutions further published the announcement on their official websites and on their social media pages (as available).

The total number of participants 139 (65 women).

Participants per occupation/groups:

- Community administrations - 60

- Regional administrations - 10

- Civil society sector - 20 people

- Tourism sector - 27

- Residents  - 22

Agenda

| Topic | Presenter |
| --- | --- |
| Welcome Remarks and Project Presentation | TC, Anahit Voskanyan |
| WB Environmental and Social Standards (ESS) and Summary of Instruments Prepared within the framework of the Project | ATDF, Knarik Grigoryan |
| ESMF and the ESCP | ATDF, Armine Gabrielyan |
| RF and LMP | ATDF, Knarik Grigoryan |
| Stakeholder Engagement Plan (SEP) | ATDF, Mary Abrahamyan |
| Questions and Answers |  |

Welcome Remarks and Introduction of Procedures

Ms. Anahit Voskanyan, Representative of the TC, welcomed the participants and expressed her appreciation to the representatives of communities, local self-government bodies, CSOs, and the private sector for their participation.

She emphasized that the TRIP would play an important role in the development of Armenian communities, as well highlighted that the Loan Agreement has already been signed with the WB and is currently undergoing ratification by the President of the RoA. The Project will be implemented with financing from the WB and co-financing from the GoA.

The main objective of the Loan is to support the development of tourism infrastructure in communities, which is expected to increase tourist flows and stimulate local economic growth.

Ms. Anahit Voskanyan presented that the Project includes seven clusters: Goris, Yeghegis, Areni, Jermuk, Gyumri, Dvin, and Dilijan. Within these clusters, it is planned to implement both infrastructure and cultural initiatives, which will contribute not only the development of the tourism sector but also the socio-economic improvement of communities. She emphasized that each sub-project will be developed through joint discussions with the respective community, and the active participation and feedback of local residents will be key to the Project’s success. It was highlighted that the draft CDPs, to be developed on the bases of Cluster Development Concepts, will be presented to the target communities for their feedback and recommendations. The importance of the PCs was emphasized for the stakeholders as a key step in ensuring the successful launch of the Project.  She also highlighted the soft components, emphasizing the significance of DMO activities, which are expected to ensure effective linkage between the generated outputs and the tourism market.

ATDF Head of ES Department Knarik Grigoryan, Environmental Specialist Armine Gabrielyan, and Social Specialist Mary Abrahamyan presented the documents prepared in accordance with WB procedures, including the ESMF, SEP , RF, LMP, and ESCP.

The Project’s Components were presented, as well as the role and importance of each in the stages of Project implementation phases. It was noted that ATDF has published announcements regarding the PCs on its official website www.atdf.am and on social networks. During PC the Stakeholder Engagement Plan, the Grievance Redress Mechanism, and the importance of timely stakeholder feedback were presented in detail. It was emphasized that all activities will be implemented in accordance with the WB’s ESSs and the legislation of the RoA. The presentation covered the procedures, as well as the mitigation measures included in the instruments.

It was highlighted that the E&S specialists of ATDF will carry out regular monitoring to construction sites to ensure that all activities are fully compliant with the approved ES instruments.

| Question | Answer | Amendment to the instruments, Operational manual and Project activities |
| --- | --- | --- |
| Dilijan |  |  |
| How will the project be financed? | The TC is responsible for the content of the Project. Once the sub-project is selected and approved, it is transferred to the ATDF, which is responsible for the implementation. The Fund organizes the expertise review, design, and procurement processes. When the sub- project package is fully prepared for implementation, financing for the sub-project’ s construction works will be initiated. | The Project Operational Manual provides a comprehensive description of the financing, subproject selection, assessment, and implementation procedures. |
| How much money is planned for the implementation of each cluster? | The planned funding for each cluster is not yet finalized and budget distribution for the clusters will be determined after the Project commences. |  |
| How will the beneficiaries be involved, when will a working group be created in the community, when will the project be launched, when will we be able to determine the sequence and priority of the projects included in the concept? | There are certain procedures that must be approved to run the Project. Only after the launch of the Project working groups will be formed in the communities. The concept includes projects, the effectiveness and expediency of which should be evaluated before their implementation. CDPs will also be developed, which will reflect the priorities of the sub-projects included in the concept, which will also be presented and discussed in the communities. One of the prerequisites for launching the Project is also this meeting, involving stakeholders, ensuring their awareness, and recording suggestions and comments to consider them. | An annex will be incorporated in the SEP outlining the procedure for establishing a Working Group, including eligibility criteria, participation mechanisms, and defined roles and responsibilities. ATDF and TC will also ensure that the establishment and operation of the Working Groups are conducted in a transparent manner and communicated in a way that is easily understandable to local communities. |
| Remark. The head of the community noted that there are lawsuits related to the Dilijan City Park, and the community plans to independently improve the park, making it accessible to residents without an entrance fee. The head of Dilijan community also noted that the municipality will reject the request for architectural and engineering design permit for the works in Central park of Dilijan. | This concern was duly noted. It was added that the Project will be implemented only on communal lands, and no activities will be carried out on private territories. The sub-projects have not been selected yet and the concern raised will be duly considered in the course of developing the Dilijan CDP. | The issues and concerns raised will be assessed and addressed during the preparation of the Dilijan CDP. |
| What tools are being developed to ensure that the loan is justified and does not become an unnecessary burden for the citizens of Armenia? | Anahit Voskanyan explained that an economic analysis is carried out before planning each sub-project. The repurchase period is calculated due to tourist flows, as well as side economic effects. If the Project does not provide the result necessary to repay the loan, even with an indirect impact, it is not executed. |  |
| Ararat Regional Administration (Dvin) |  |  |
| There is an archaeologists’ shelter in the area of Dvin Museum which is currently in poor condition. Which actions are planned? This shelter will be dismantled or will be preserved? In addition we propose to dismantle the shelter, as the presence of the structure may adversely affect the overall appearance and aesthetic value of the archaeological site. | The sub-project design must be updated; however, based on the approved design that has undergone expertise, the archaeologists’ shelter will be dismantled, and the newly constructed museum will include a designated section for the accommodation of the archaeologists. | The issue raised will be further discussed with all the stakeholders including the community administration and the “Service for the Protection of Historical Environment and Museum-Reserves” SNPO and addressed under the revision of the design documents. |
| Why is the management of this facility transferred to the community upon completion of the works and not to the regional administration, the state, or the TC? /Regional administration employee/ | The Dvin Museum reserve area is under the jurisdiction of the Ministry of Education, Science, Culture, and Sports. The operation will be transferred to the state non-profit organization, Service for the Protection of Historical Environment and Museum-Reserves. The implementation of the Dvin cluster is expected to contribute not only to the development of the Hnaberd settlement but also to neighboring communities and the broader region. The reconstructed and restored infrastructure will support local business development, increase tourist flows, and foster the growth of small and medium-sized enterprises. |  |
| Are similar projects planned to be implemented in Masis community? | Currently, no works are planned in Masis community under the Project. | The scope of the Project including the selected Clusters and the selection criteria will be presented in the Project Operational manual. |
| It was recommended to increase investments in Ararat region, as it contains numerous archaeological and historical-cultural sites. The restoration and revitalization of these sites would stimulate tourism development and will increase visitor flows. | The proposal was recorded by the TC representative to be taken into account in the further projects and initiatives. |  |
| Vayots Dzor Regional Administration (Jermuk, Areni, Yeghegis) |  |  |
| The residents expressed their enthusiasm about the tourism development Project in their community and were interested in making investments. However, they also have concerns, about the mining geological investigation which is currently in progress in the Vardahovit community. Although it has not yet been determined whether a mine will be opened, and they sincerely hope that the investment will stimulate tourism development and that priority will be given to this way rather than to potential future mining operations./Resident/ | The representatives of the ATDF asked to clarify the information. It was noted that the envisaged mine is located approximately 15 km far from the village Goghtanik and is still in the exploration stage. The concern was duly noted. Local government representatives added that they are against the exploitation of the mine and are in favor of the development of tourism, which will contribute to the well-being of the residents. | Additions will be made in the Yeghegis CDP and the related E&S assessments. |
| The other participants also noted that their preference is tourism development. They mentioned that certain investments have already been made and expressed hope that priority will be given to tourism development. | The Regional Administration staff stated that they have several strategic directions aimed at the development of the Region, and tourism development is the top priority. Although the Geological exploration has not been banned, however, whether a mine will be opened or not depends on local self-government’s decisions. Tourism development will help enhance people’s well-being, which remains their primary goal. |  |
| Goris |  |  |
| The Deputy Head of the Community expressed her gratitude and highlighted that several projects have already been implemented in Goris with the support of the WB, including the restoration of streets and the facades of historic houses. She emphasized that the community is well informed about the E&S impacts due to such initiatives. Furthermore, she proposed the restoration of ancient cultural buildings and the river cleaning. She also suggested the rehabilitation of the road leading to Old Khndzoresk, as well as the inclusion of infrastructure development works in Old Khot, Shinuhayr, and Halidzor settlements within the Project. | Each subproject will be chosen according to the following procedures: a working group will be formed in the Community. The approved packages will be submitted to the MoE for economic evaluation and assessment. Effective and successful subprojects are submitted to the Project Management Committee, chaired by the Deputy Prime Minister. Upon approval, the subprojects receive financing. These steps are designed to ensure the funding of initiatives that are both successful and economically efficient. Communities are also encouraged to provide accurate and reliable data, which will be the key to proper project planning. | The information provided by the community will be used to guide and inform the planning and prioritization of subprojects within the Project. Specifically, the data on local needs and proposed initiatives will help the team identify potential investment areas that align with the Project’s objectives and selection criteria. This information will also support the preparation of ES assessments, technical designs, and cost-benefit analyses, ensuring that proposed sub-projects are both relevant to community priorities and consistent with the Project’s development goals. |
| Goris is an ancient city with a historical CH including numerous caves and traditional olive presses. It is proposed to restore the caves and the local olive press, which would be presented to tourists as a tangible and revitalized part of history. /Tour guide/ | Prior to initiating any activity at a historical or cultural site, extensive archaeological excavations and research studies are required, which are often time-consuming and resource-intensive. Given the limited implementation period of the TRIP, such complex and lengthy subprojects cannot be accommodated within the current Project timeframe. | The proposals submitted by the community — particularly those related to the restoration of cultural heritage assets and similar initiatives — are valuable and may be considered for inclusion under future or complementary programs implemented by the Government or other development partners. Communities are therefore encouraged to formally submit these ideas to the TC for potential integration into upcoming initiatives. |
| We are aware that the road leading to the 'Swinging Bridge' in Khndzoresk has already been designed. Does this mean the project will be implemented sooner? /Entrepreneur/ | The design will be updated; however, if it is included in the Project, its implementation will be prioritized and completed more quickly than the others. | The community administration and relevant stakeholders, including representatives of CSOs and the private sector, will be kept informed throughout the preparation of the Goris CDP. |
| The participants proposed expanding the Projects in Syunik, highlighting the presence of numerous border communities. They emphasized that such an expansion would foster tourism development and economic growth, thereby helping to discourage outmigration from these communities. | The proposal was recorded by the TC representative to be taken into account in the further projects and initiatives. |  |
| Gyumri |  |  |
| Is there any instrument or mechanism to address cases where, despite having received compensation and vacated the area, the affected person later resumes activities in the same location? / Regional Governor’s Advisor | The WB’s ESS5 addresses this issue through the establishment of a “cut-off date”, which marks the point at which all affected persons and impacts are recorded. Any new activities, claims, or changes occurring after the cut-off date are not eligible for compensation or other entitlements unless otherwise agreed. The cut-off date is formally announced, typically through public notices in the community and direct notification of affected persons. A similar provision exists under the legislation of the RoA, which governs compulsory acquisition and compensation processes. This legal framework ensures that once compensation has been received and the area vacated, any subsequent activities in the same location are not eligible for further compensation. Therefore, the mechanism is preventive: the “cut-off date” and the final settlement of compensation create legal certainty, ensuring that obligations of the state and project are closed with respect to that parcel of land or other asset. | Detailed descriptions of the resettlement impact assessment procedures and the “cut-off date” mechanism are provided in the Project RF. |
| Are there any preliminary designs available at the moment? | Before the loan agreement was finalized, numerous consultations were held with the communities, local businesses were reviewed, and sub-projects were identified in line with agreed principles for inclusion in the Cluster Development Concepts. Some of these proposed sub-projects will subsequently be integrated into the CDPs to be prepared and implemented during the next phases. After the Project launches, all projects, and possibly new ones, will be discussed within the communities according to priority and effectiveness. The loan Projects must yield significant returns, undergo proper calculations, be economically efficient, and have all components evaluated. The design for the works in the territory of Dashtadem Fortress, included in the previous LEID Project, also needs to be updated. The design for the sub-project will be considered for update only after the land issues are regulated. | The Project Operational Manual provides a comprehensive description of the financing, subproject selection, assessment, and implementation procedures. |
| Will the Project also cover the replacement of equipment and furniture (e.g., in the case of museum renovation)? | Yes, the replacement of a museum equipment/furniture can also be included. |  |
| When is the Project launch planned? /Regional Governor’s Office/ | The Loan Agreement was signed The Project has officially started, but the implementation would begin in about a month, after the completion of the necessary procedures to become effective are completed. The process for regulating the working groups is currently being developed and will be finalized soon. For each cluster, an appropriate working team will be selected to discuss the priority steps. |  |
| In the LEID Project, the restoration of Dashtadem Fortress was planned. Is it intended to be included in the TRIP Project, and if so, will it be updated? /Head of Dashtadem Administration/ | Yes, the project is included but the design needs to be reviewed and updated with the Community as well. It is critically important to resolve the land issue, which is a prerequisite for reviewing the design. |  |
| The regional office expressed interest in participating in the working groups. | The initiative was welcomed, with noting that further details on the establishment of a Working Group and participation mechanisms will be shared with the community, regional administration offices, and other stakeholders. ATDF representatives welcomed the proposal and assured that communities would be informed in advance about all meetings and discussions. There will be meetings with design consultants and architects, and the designs and infrastructure restoration working documents will be discussed in detail at the appraisal stages to avoid future problems as much as possible. | An annex will be incorporated in the SEP outlining the procedure for establishing a Working Group, including eligibility criteria, participation mechanisms, and defined roles and responsibilities. |
| Suggestion/Recommendation During the development of the Project, special attention should be given to the design of buildings of historical and cultural value, as well as their surrounding areas. The foundations of such buildings are often in unfavorable conditions, and during restoration, basements may end up higher or lower than the street’s zero level due to street works. Additionally, the windows of semi-basement floors may remain below grade, which puts the entire architectural and structural integrity of the building at risk. /Director of the "Kumairi" Historical and Cultural Reserve-Museum SNCO/ | It was noted that during the design stage, technical solutions for sensitive sections including measures to preserve hydro-technical features and protect historical and cultural buildings will be incorporated; ensuring appropriate “no-damage” measures are considered for review by the SNCO. | The issue raised will be duly considered during the preparation of the Gyumri CDP and the related design documents under the Cluster. |

Following questions and proposals

Following the PCs, a five-day period was provided for submitting questions or proposals. Within this timeframe, a letter was received from a resident of Yeghegis community, Vayots Dzor region. The summaries of the received letter and the answer are provided below.

The summary of the letter received

The letter highlights that while the TRIP is intended to support sustainable economic development, its objectives may be undermined by parallel mining projects in Vayots Dzor. Specific risks mentioned include the resumed preparatory works at the Amulsar gold mine, ongoing exploration at Vardahovit, operations at Zaritap, and recently granted permissions for mining activities at Azatek.

The letter stresses that mining operations are incompatible with both the rich cultural heritage and the eco-tourism potential of Vayots Dzor. Concern was expressed that such developments could make the region unsuitable for tourism and habitation, thereby jeopardizing not only local livelihoods but also Armenia’s broader tourism strategy. In addition, questions were raised about the prudence of taking on a WB loan for tourism development if mining activities threaten to compromise the Project’s results and the country’s repayment capacity.

In conclusion, the letter recommends that the TC develop a clear eco-tourism strategy for Vayots Dzor, integrated with agriculture and winemaking. This strategy should be communicated to local communities through participatory consultations, ensuring awareness of sustainable alternatives to mining. Such an approach would help safeguard tourism development, build community support, and maximize the long-term benefits of the WB project.

The summary of the answer letter of the MoE

“The information presented in writing has been shared with the ATDF and included in the minutes of the PC on the E&S Framework Documents of the TRIP.

At the same time, we note that the project has not yet commenced. Following its launch, a working group will be established for the implementation of each cluster, within which the raised issues will be discussed to ensure the effective implementation of the Project to the extent possible”.

Please see details here: https://winnetarmenia.org/en

Vulnerable status may stem from an individual’s or group’s race, national, ethnic or social origin, color, gender, language, religion, political or other opinion, property, age, culture, literacy, sickness, physical or mental disability, poverty or economic disadvantage, and dependence on unique natural resources.

http://atdf.am/uploads/reports/ESMF.pdf

http://atdf.am/uploads/reports/SEP.pdf

http://atdf.am/uploads/reports/RF.pdf

http://atdf.am/uploads/reports/ESCP.pdf

http://atdf.am/uploads/reports/LMP.pdf

The SE activities for CDP preparation plan will be revised for the final SEP according to the Gender analysis implemented in the framework of the Project

Section 6.4 of the ESMF has been updated to include provisions on air pollution (PM level) as well noise measurement.

Agenda remained consistent across all the PCs covered under the minutes.